## Sheet1
Feature | Priority (1 = Needed, 2 = On-Going, 3 = Tenative, 4 = Luxury Features) | Complexity [On a scale of 1 to 5] (1 = Simple and 5 = Complex) | Estimated Time Cost | Feature Implementer
Task List Creation by Admin | 1 | 3 | 2-5 days | Doug, assisted by Sherman
Task List Attending by User | 1 | 4 | 2-5 days | Doug
Multi-Day Scheduling (from POV of Admin) | 1 | 5 | 5-6 days | Xianye
Multi-Day Scheduling (from POV of User) | 1 | 4 | 5-6 days | Xianye
File IO Changes | 1 | 2 | 2-4 days | William
Bug Fixing | 2 | 2018-01-05 | 1-10 days | Anyone as Needed
UI Improvements | 2 | 4 | 1-10 days | Anyone as Needed
Document What is Undocumented | 3 | 2 | 1-5 days | Anyone as Needed
Use C++ Boost to More Validate Dates | 3 | 3 | 1-2 days | Sherman if Allowed